## How to use
How to use this tool
Signature Aviation ¦ PM and CM Toolkit ¦ Full tier
What it is
Complete all items before formally closing the project.
When to use it
At the end, once the solution is stable in BAU.
When not to use it
At go live. Closure comes after hypercare settles.
How to fill it in
1. Work through every closure item. 2. Confirm handover is complete. 3. Capture lessons learned. 4. Get sponsor sign off to close.
Time needed
1 hour
What good looks like
A clean close with nothing left hanging and ownership clearly handed over.
Related tools
Lessons Learned, Support Handover, Governance Framework

## Project Closure Checklist
Project Closure Checklist ¦ Wake Forest University
Complete all items before formally closing the project.
Category | Checklist item | Owner | Status | Completed date | Notes
Handover | Onboarding materials updated for new starters | Change lead | Not started
Handover | Support team briefed with FAQ and known issues | Change lead | Not started
Handover | Governance model confirmed and owner identified | PM | Not started
Comms | Final all-staff communication sent | Comms lead | Not started
Documentation | All project docs archived in shared folder | PM | Not started
Documentation | Decision log complete and stored | PM | Not started
Documentation | Lessons learned report written | PM | Not started
Review | PIR presented to sponsor and leadership | PM | Not started
Review | User survey completed and analyzed | Change lead | Not started
Review | Adoption metrics confirmed above target | Change lead | Not started
Close | Sponsor sign-off on project closure | PM | Not started
Close | 6-month health check reminder set | PM | Not started
Close | Team recognized and thanked | PM | Not started