## How to use
How to use this tool
Signature Aviation ¦ PM and CM Toolkit ¦ Full tier
What it is
Combined project and change management milestones. Update status weekly.
When to use it
After the charter is agreed, as the working plan throughout.
When not to use it
As a charter or scope doc. Those come first.
How to fill it in
1. List milestones for both project and change. 2. Set dates and owners. 3. Update status weekly. 4. Flag slippage early.
Time needed
1 to 2 hours to build
What good looks like
One plan that shows both delivery and adoption on track.
Related tools
Project Charter, RAID Log, Status Update deck

## Project Plan
Project Plan ¦ Wake Forest University
Combined project and change management milestones. Update status weekly.
# | Phase | Milestone | Type | Owner | Start | Target date | Actual date | Status | Dependencies | Notes
1 | 0. Planning | Define scope and write project charter | PM | [Name] | [Date] | [Date] |  | Not started
2 | 0. Planning | Define project team and roles | PM | [Name] | [Date] | [Date] |  | Not started | 1
3 | 0. Planning | Identify stakeholders | CM | [Name] | [Date] | [Date] |  | Not started | 1
4 | 0. Planning | Create project plan and timeline | PM | [Name] | [Date] | [Date] |  | Not started | 1, 2
5 | 0. Planning | Kick-off meeting | PM | [Name] | [Date] | [Date] |  | Not started | 4
6 | 0. Planning | Set up governance and comms | CM | [Name] | [Date] | [Date] |  | Not started | 3
7 | 1. Discovery | Map current state (as-is) | PM | [Name] | [Date] | [Date] |  | Not started | 5
8 | 1. Discovery | Identify impacted processes, users, systems | PM | [Name] | [Date] | [Date] |  | Not started | 7
9 | 1. Discovery | Stakeholder and impact assessment | CM | [Name] | [Date] | [Date] |  | Not started | 3, 7
10 | 2. Design | Design future state | PM | [Name] | [Date] | [Date] |  | Not started | 7, 8
11 | 2. Design | Define governance, policies, RACI | PM | [Name] | [Date] | [Date] |  | Not started | 10
12 | 2. Design | Launch communication plan | CM | [Name] | [Date] | [Date] |  | Not started | 9
13 | 3. Build | Build system config and process changes | PM | [Name] | [Date] | [Date] |  | Not started | 10, 11
14 | 3. Build | Develop training materials and plan | CM | [Name] | [Date] | [Date] |  | Not started | 12
15 | 4. Test | Test with real users (UAT) | PM | [Name] | [Date] | [Date] |  | Not started | 13
16 | 4. Test | Deliver training and track completion | CM | [Name] | [Date] | [Date] |  | Not started | 14
17 | 5. Go-live | Go-live readiness check and launch | PM | [Name] | [Date] | [Date] |  | Not started | 15, 16
18 | 5. Go-live | Hypercare support active | CM | [Name] | [Date] | [Date] |  | Not started | 17
19 | 6. Close | Post-implementation review | PM | [Name] | [Date] | [Date] |  | Not started | 18
20 | 6. Close | Embed change and transition to BAU | CM | [Name] | [Date] | [Date] |  | Not started | 19