## How to use
How to use this tool
Signature Aviation ¦ PM and CM Toolkit ¦ Full tier
What it is
Risks, Assumptions, Issues, and Dependencies in one running list. See the Legend tab for what each type means.
When to use it
From planning onward, reviewed at every check in.
When not to use it
For decisions already made. Use the Decision Log for those.
How to fill it in
1. Log each item under the right type. 2. Set impact, owner, and a response. 3. Update status at every check in. 4. Escalate anything high impact early.
Time needed
20 minutes to start, then ongoing
What good looks like
A live list where nothing high impact sits without an owner.
Related tools
Issue Tracker, Decision Log, Action and Decision Log

## RAID Log
RAID Log
Risks, Assumptions, Issues, and Dependencies. One running list of everything to keep an eye on. See the Legend tab for what each type means.
ID | Type | Description | Impact | Likelihood | Owner | Response or plan | Status | Due date | Notes
R1 | Risk | Key role may not be filled in time | High | Medium | [Owner] | Start recruiting now; line up a short-term backup | Open | [Date] | Review weekly
A1 | Assumption | Current data is accurate enough to migrate | Medium | — | [Owner] | Confirm with a sample check before go-live | Open | [Date] | Becomes a risk if wrong
I1 | Issue | Test environment is not ready | High | — | [Owner] | Raised with IT; target fix this week | In progress | [Date] | Blocking testing
D1 | Dependency | Need sign-off from Finance before launch | High | — | [Owner] | Meeting booked; sign-off requested by [date] | Open | [Date] | On the critical path

## Legend
RAID Log · Legend and how to use
What RAID means
Risk | Something that might happen and would hurt the project. Log it early and plan for it before it happens.
Assumption | Something you are taking as true for now. If it turns out to be wrong, it often becomes a risk or an issue, so check it.
Issue | Something that has already happened and needs dealing with now. Issues are live problems, not maybes.
Dependency | Something this project needs from someone else, or that others need from you. Track it so a handoff does not slip.
Impact · how much it would hurt
High | Would seriously affect cost, timeline, scope, or people. Needs attention and a clear owner now.
Medium | Would cause real disruption but is manageable with planning.
Low | Minor effect. Worth noting, but not urgent.
Likelihood · for risks, how probable it is
High | More likely than not to happen.
Medium | Could reasonably go either way.
Low | Unlikely, but still worth tracking.
Note | Likelihood applies to risks. For assumptions, issues, and dependencies you can leave it blank or use a dash.
Status
Open | Logged and being watched, but no action started yet.
In progress | Someone is actively working the response or plan.
On hold | Paused for now, with a reason noted.
Closed | Resolved, no longer happened, or no longer relevant. Keep it in the log for the record.
How to use this log
1 | Add a row whenever something could affect the project. Pick the Type from the dropdown.
2 | Give it a short, plain description, an Impact, an Owner, and a Response or plan.
3 | Review the open rows at your regular check-in. Update Status as things move.
4 | Pull the few that matter most into your Status Update each period. This log is the full record; the status report is the highlight reel.
5 | The first four rows are examples in grey. Type over them or delete them to start your own.