## How to use
How to use this tool
Signature Aviation ¦ PM and CM Toolkit ¦ Full tier
What it is
Estimate hours by role and phase. Blue cells are inputs; subtotals calculate automatically.
When to use it
During planning, to size and justify the resource ask.
When not to use it
For tracking actual time. This is an estimate.
How to fill it in
1. Enter hours in the blue input cells. 2. Let subtotals calculate. 3. Compare against the benchmarks tab. 4. Use the output to justify resourcing.
Time needed
1 hour
What good looks like
A defensible hours estimate you can take to a sponsor.
Related tools
Project Plan, Project Charter, Team Roster

## Hour Estimate by Role
Hour Estimate by Role
Blue cells are inputs. Subtotals and totals calculate automatically.
Role | Discovery & Scope | Design & Planning | Implementation | Post Go-Live & Sustain | Role Total
PROJECT TEAM ROLES
Project / Program Lead | 6 | 8 | 12 | 6
Change Lead | 8 | 8 | 10 | 8
Functional Consultant | 0 | 8 | 8 | 0
Comms Lead | 0 | 4 | 0 | 0
Training Lead | 0 | 0 | 8 | 0
QA / Test Lead | 0 | 0 | 6 | 0
Project team subtotal
SUBJECT MATTER EXPERT ROLES
Process / Area SMEs | 16 | 20 | 32 | 16
Functional SMEs (HR, Security, Reporting, Data) | 4 | 5 | 8 | 0
Super Users | 0 | 0 | 0 | 0
SME subtotal
TOTAL HOURS

## Benchmarks
Benchmark Hours by Impact Level
Typical effort ranges to sanity check your estimate. Use the closest level as a starting point.
Impact Level | Hours Type | Discovery & Scope | Design & Planning | Implementation | Post Go-Live & Sustain | Total
Low | Project team | 4 | 3 | 3 | 2
| SME | 4 | 3 | 3 | 2
Medium | Project team | 14 | 28 | 44 | 14
| SME | 20 | 25 | 40 | 16
High | Project team | 52 | 90 | 110 | 36
| SME | 56 | 80 | 150 | 60

## Meeting Plan
Meeting Plan
List the meetings for each phase, who runs them, and who attends.
Phase | Meeting | Purpose | Owner | Attendees | Cadence | Duration
Discovery & Scope | Kickoff and scope session | Align on scope, sponsor, and impact | Project Lead | Project team, sponsor | Once | 90 min
Discovery & Scope | Stakeholder mapping workshop | Identify and rate stakeholders | Change Lead | Project team, key SMEs | Once | 60 min
Design & Planning | Design sessions | Shape the future state | Functional Lead | SMEs, functional team | 2 to 4 sessions | 60 to 90 min
Design & Planning | Change and comms planning | Plan engagement and messages | Change Lead | Change Lead, comms | Once | 90 min
Implementation | Project check-in | Track progress and blockers | Project Lead | Project team | Weekly | 30 to 45 min
Implementation | UAT review and sign-off | Confirm the build works | Functional Lead | SMEs, QA | 1 to 2 sessions | 60 min
Implementation | Readiness review | Confirm ready to launch | Project Lead | Project team, sponsor | Before launch | 60 min
Post Go-Live & Sustain | Hypercare standup | Resolve early issues fast | Project Lead | Project team, support | Several per week | 15 min
Post Go-Live & Sustain | Adoption review | Check adoption and benefits | Change Lead | Change Lead, owners | Monthly | 45 min
Post Go-Live & Sustain | Lessons learned | Capture what to repeat or improve | Project Lead | Project team, sponsor | Once | 60 min