## How to use
How to use this tool
Signature Aviation ¦ PM and CM Toolkit ¦ Full tier
What it is
Assess how significantly each stakeholder group is affected by the change.
When to use it
During planning, to focus support where impact is highest.
When not to use it
For a broad process and system view. Use the Change Impact Assessment.
How to fill it in
1. List each stakeholder group. 2. Rate the size of the impact. 3. Note specific concerns. 4. Plan support for the most affected.
Time needed
45 minutes
What good looks like
Support effort aimed at the groups the change hits hardest.
Related tools
Change Impact Assessment, Stakeholder Register, Training Plan

## Stakeholder Impact Assessment
Stakeholder Impact Assessment ¦ Wake Forest University
Assess how significantly each stakeholder group is affected by the change.
Stakeholder group | # of people | How much daily work changes | Compliance / legal implications | Risk if not adopted | Experience with this type of change | Overall impact | Key concerns | CM approach
[Group A - e.g. HR team] | [#] | Moderate - noticeable workflow changes | No compliance | Moderate - inefficiency | Some experience | Medium | [Validated concerns] | Targeted comms + training
[Group B - e.g. Finance] | [#] | Major - fundamentally different | Internal governance | High - financial risk | No experience | High | [Validated concerns] | Intensive comms + training + hypercare
[Group C - e.g. Managers] | [#] | Minor - small adjustments | No compliance | Minimal | Done this before | Low | [Validated concerns] | Announcement + FAQ

## Instructions
How to use this template
Score each group based on the 5 impact questions in the CM & PM 101 tool.
High impact groups need dedicated CM attention: personal communications, hands-on training, and extended hypercare.
Medium impact groups need structured comms and targeted training.
Low impact groups need a clear announcement and FAQ document.