## How to use
How to use this tool
Signature Aviation ¦ PM and CM Toolkit ¦ Full tier
What it is
Track training design, delivery, and completion. Completion percent auto calculates.
When to use it
From training design through go live.
When not to use it
For a quick readiness confirmation. Use the Training Readiness Plan.
How to fill it in
1. Plan content and audiences. 2. Schedule delivery. 3. Track completion. 4. Target the agreed threshold before go live.
Time needed
1 to 2 hours to build
What good looks like
Training designed, delivered, and tracked to a clear completion target.
Related tools
Training Tracker, Training Content Audit, Training Readiness Plan

## Training Plan
Training Plan ¦ Wake Forest University
Track training design, delivery, and completion. Completion % auto-calculates.
Training module | Audience | Format | Duration | Owner | Delivery date | # Invited | # Completed | Completion % | Status | Notes
Overview: why this change | All staff | Email / video | 5 min | Change lead | [Date] |  |  |  | Not started | Send before any detailed training
Manager briefing | All managers | Live workshop | 60 min | Change lead | [Date] |  |  |  | Not started | Run before all-staff sessions
Role training: [Role A] | [Team A] | Workshop / sandbox | 2 hrs | Training lead | [Date] |  |  |  | Not started | Role-specific tasks only
Role training: [Role B] | [Team B] | Workshop / sandbox | 90 min | Training lead | [Date] |  |  |  | Not started
Quick reference guide | All users | PDF / Google Site | Self-serve | Training lead | [Date] | N/A | N/A | N/A | Not started | Publish 2 wks before go-live
Refresher drop-in session | All users | Live webinar | 30 min | Training lead | [Date] |  |  |  | Not started | Week 2 of hypercare
New-starter induction module | New starters | E-learning | 45 min | Training lead | [Date] | N/A | N/A | N/A | Not started | Update before project closes