Wake Forest University

Project Management and

Change Management Toolkit

A practical guide to leading projects and change at Wake Forest, sized to fit whatever you are taking on.

MenuSections

Begin

1Start here 2Size up your project

Set up for success

3Governance & approvals 4Roles & responsibilities 5The project lifecycle 6Leading change

Do the work

7Templates & tools 8AI prompt library 9Advanced toolkit

No prior project management experience needed. Everything here is written for first timers.

Wake Forest University · Pro Humanitate

# Project Management and Change Management Toolkit

These tools help all Wake Forest staff define and run projects, whatever their size. They are grounded in established project and change management practice and provided as editable Google Workspace templates, so you can adapt them to your own work. Use them on technical and non-technical projects, with or without prior experience.

Start here

### New to running a project, or not sure where to begin? Answer three quick questions and we will tailor your first steps, the help to line up, and your starter templates.

Back Next

Explore the toolkit

01Size up your projectMatch the planning, governance, and rigor to the size and complexity of the work. 02Governance and approvalsWho gives the go ahead, who you report to, and how often. 03Roles and responsibilitiesWho does what, from sponsor and project lead to stakeholders. 04The project lifecycleThe stages every project moves through, from kickoff to close. 05Leading changeHelp people get ready, willing, and able for what is changing. 06Templates and toolsReady to use documents you can fill in, in editable Google Workspace formats. 07AI prompt libraryPrompts to draft plans, communications, and updates with AI. 08Advanced toolkitDeeper templates and reference material for experienced leads.

New to these words? Open the plain-English glossary Project leadYou, most likely. The person running the project day to day. SponsorThe senior person who backs your project, finds the money, and clears roadblocks. Your go-to when you are stuck. StakeholderAnyone affected by the project or who cares how it turns out. ScopeWhat the project will and will not cover. Writing it down keeps the project from quietly growing. CharterA one page document that says what you are doing, why, and who is involved. It gets the project the go ahead. MilestoneA meaningful checkpoint, like "design approved" or "go live." Steering groupA small group of leaders who approve the big decisions. RACIA simple chart of who does each task: who is Responsible, Accountable, Consulted, and Informed. RAID logA running list of Risks, Assumptions, Issues, and Dependencies. A fancy name for "things to keep an eye on." ADKARThe five stages people go through to accept a change: Awareness, Desire, Knowledge, Ability, Reinforcement. PMOProject Management Office. The central team that sets the standards and can support bigger projects. Stage gateA checkpoint between stages where someone confirms it is OK to keep going.

Step 2

## Size up your project

Experienced teams right-size their approach: they match the level of planning, governance, and rigor to the size and complexity of the work. We group projects into three tiers, so you apply just enough structure and never more than the job needs. Knowing your tier also gives everyone a common language for the work.

Tier 1 · Small light touch

Well suited to a first-time lead, a coordinator, or anyone new to running projects

This sounds like you if

- It mostly involves you and your close team

- Fewer than about 25 people are affected

- Only your manager is watching

- Nothing major is being rebuilt

What you need

- A short list of who is involved

- A simple project plan

- A quick weekly update

- A closeout checklist at the end

Tier 2 · Medium standard

Best run by someone with a project or two behind them, or with a mentor alongside

This sounds like you if

- A few teams or departments are involved

- Roughly 25 to 500 people are affected

- A director or senior leader is watching

- Some ways of working will change

What you need

- A full project plan and charter

- A plan for keeping people informed

- A risk list

- A simple group that approves decisions

Tier 3 · Large major project

Standard practice is to lead or co-lead with an experienced project manager or the project office

This sounds like you if

- It reaches across the whole organization

- 500 or more people are affected

- Top leadership is watching

- Technology, process, and people all change

What you need

- A senior sponsor and a steering group

- Experienced project and change support

- A clear plan with checkpoints

- A way to track the benefits afterward

Step 3

## Governance: who decides and approves

Governance is simply who gives the go-ahead, who you report to, and how often. The larger the project, the more formal it becomes. Match it to your tier.

| If your project is | You need | You report to | How often |
| --- | --- | --- | --- |
| Small | One person who backs it, plus a simple update | Your manager | Monthly, or when something changes |
| Medium | A backer plus a small group that approves decisions | A director or senior leader | Every two to four weeks |
| Large | A senior steering group and formal checkpoints | Top leadership | Monthly with leadership, weekly with the team |

### Plain words for common roles

Sponsor

The senior person who backs the project, secures the money, and clears roadblocks.

Steering group

A small group of leaders who approve big decisions and keep the project on track.

Project lead

You, most likely. The person running the project day to day.

Checkpoint

A moment between stages where someone confirms it is OK to keep going.

Step 4

## Roles and responsibilities

These jobs show up on almost every project. On a small one, the same person often wears several hats. That is fine, just make sure each job is covered.

| Job | What they look after |
| --- | --- |
| Sponsor | Backs the project, finds the money, removes blockers |
| Project lead | Runs the project day to day, tracks progress, keeps people updated |
| Steering group | Approves big decisions and changes |
| Business owner | The person who will live with the result and cares it works |
| Change lead | Helps people get ready for and accept the change |
| Experts | People who know the detail and help figure out how things should work |

### A simple way to share out the work

For each task, decide who actually does it, who signs off on it (just one person), who you should ask for input, and who simply needs to be kept in the loop. Project managers call this a RACI chart, but you do not need the jargon to use the idea.

Step 5

## The project lifecycle

Almost every project, large or small, moves through these seven stages in order. You will not need every one on a small project, but it helps to see the whole path.

1

Get the go ahead

Agree what you are doing and why, and get it approved.

2

Plan it

Line up the team and make a simple plan.

3

Look into it

Understand how things work today.

4

Design it

Decide how things should work instead.

5

Build it

Make it and test it on a small scale first.

6

Launch it

Go live, and help people through the switch.

7

Check it worked

See if it delivered, and note what to do better.

### What to do first, every time

- Write down what you are doing and why, on one page. Get someone senior to agree to it.

- List who is involved and who is affected.

- Set a regular check-in so progress and problems surface early.

- Use the templates in section 7 for each step. The questions in section 1 tell you which ones you need.

Step 6

## Leading change

1Understand

What change management is, and the path you will follow

Projects deliver something new. Change management helps people actually use it. You can install a system or roll out a new process perfectly and still fall short if people do not adopt it. Change management is the work of bringing people along: helping them understand the change, get ready for it, and stick with it.

Good change follows the same path whether your project is small or large. These are the six moves. They line up with the five adoption stages (ADKAR) used elsewhere in this toolkit: the moves are what you do, the stages are what people experience.

AssessAnswer a few questions to find how much change support your project needs.

PlanGet the meetings, people, and hours by role and phase.

ExecuteFollow a step-by-step checklist, with the right template at each step.

2Assess your project

Tell us about your project

There are no wrong answers. Pick the closest fit for each. We use your answers to size the right level of change support, not to grade the project.

Beginner Advanced

Show my plan

3Plan

Your plan: people, meetings, and hours

Compare: Low Medium High

Estimated hours by role and by phase

A starting estimate you can adjust. The Resource and Meeting Plan template has this same grid as an editable spreadsheet.

4Execute

Do it, step by step

Work through each phase in order. Tap a box to check off a step. Each step links the template you need. Beginner shows the essentials; switch to Advanced for the full checklist.

Your starter templates

Each link opens the matching file in the shared WFU CM and PM Templates library in Google Drive. Make your own copy before editing so the master template stays clean.

Step 7

## Templates & tools

Ready to use documents, grouped by the step they belong to. Open one, fill in the blanks, and you are done.

Each template links to its file in the shared WFU CM and PM Templates library in Google Drive.

Step 8 · A favorite

## AI prompt library

Copy one of these into an AI assistant and fill in the parts in brackets. It turns a blank page into a first draft in seconds.

Step 9 · Advanced toolkit

## The advanced toolkit

For seasoned leads running medium and large projects. This is the deeper, click-through edition: classify the work, pick a governance model, walk the milestones, and pull the full template suite for every phase.

### Classify the work, then run its playbook

Most initiatives are one dominant type. Your type sets the baseline deliverables and governance.

Technical / system

New or changed app, integration, platform, or infrastructure

Heavier discovery, a formal design, and a careful, tested cutover. Architecture review and a change advisory board approve the build and release.

Policy

A new or revised rule people must follow

Legal and risk review is a mandatory gate, and attestation and rollout matter as much as the wording.

Process

A redesigned set of steps, hand-offs, and controls

Map the current state, design the future state, and pilot before you scale. SOPs and training carry the change.

Org / team structure

A change to structure, reporting lines, or where work sits

Confidential stakeholder work, legal or works-council consultation, and careful sequencing of announcements.

### Governance model selector

| If the work is | Use | Who decides |
| --- | --- | --- |
| Small, personal, or a quick task | Light | Do it well and lightly, do not drown it in governance |
| Several teams or a shared process | Medium | A small steering group, one lead per affected team |
| Enterprise-wide or multi-division | Full | Executive sponsor, steering committee, PMO oversight, stage gates |

### Full template suite, by phase

### Change management (ADKAR) kit

Run the people track in parallel: case for change and communications (Awareness), sponsor roadmap and stakeholder impact assessment (Desire), training plan and content audit (Knowledge), training tracker and job aids (Ability), and adoption survey and lessons learned (Reinforcement).

### Glossary and acronyms

CharterThe one document that authorizes a project and names its purpose, scope, sponsor, and budget. SponsorThe senior person who backs the project and owns its success. RAID logA running list of Risks, Assumptions, Issues, and Dependencies. RACIResponsible, Accountable, Consulted, Informed. A chart of who does what on each task. ADKARAwareness, Desire, Knowledge, Ability, Reinforcement. A model for guiding people through change. OCMOrganizational Change Management. The discipline of preparing and supporting people through a change. UATUser Acceptance Testing. Checking the build does what users actually need before go live. PMOProject Management Office. The central team that sets project standards and supports big efforts. Stage gateA checkpoint between stages where someone approves the project to continue.