## How to use
How to use this tool
Signature Aviation ¦ PM and CM Toolkit ¦ Starter tier
What it is
Know your audiences. Rate influence and interest, then plan how to engage each one.
When to use it
Early, right after the charter, and refresh it as new people get involved.
When not to use it
For tracking detailed contact history. Use the full Stakeholder Register for that.
How to fill it in
1. List every group or person affected. 2. Rate influence and interest high or low. 3. Decide an engagement approach for each. 4. Review monthly.
Time needed
30 minutes
What good looks like
Every key person placed, with a clear plan for the high influence, high interest group.
Related tools
Stakeholder Register, Communication Plan, Change Impact Assessment

## Template
Stakeholder Map
Know your audiences. Rate influence and interest, then plan how to engage each one.
Name or Group | Role | Influence (H/M/L) | Interest (H/M/L) | Current Sentiment | Desired Sentiment | Engagement Approach | Owner
Sponsor | Executive sponsor | High | High | Supportive | Champion | Brief weekly, ask to visibly advocate | Change Lead
Front-line staff | End users | Low | High | Unsure | Engaged | Demos, Q and A, early involvement | Change Lead