SIGNATURE AVIATION    |    PM AND CM TOOLKIT

Training and Readiness Plan

Starter tier    |    How to use this template

What it is

A short plan that confirms training is designed, scheduled, and ready before go live.

When to use it

In the lead up to go live, alongside the readiness checklist.

When not to use it

For tracking who completed training. Use the Training Tracker.

How to fill it in

1.  Confirm content is built and reviewed.

2.  Confirm sessions are scheduled.

3.  Confirm trainers and access are ready.

4.  Flag any gaps to the readiness review.

Time needed

30 minutes

What good looks like

Training confirmed ready well before go live, with no last minute scramble.

Related tools

Training Plan, Training Tracker, Readiness Checklist

WAKE FOREST UNIVERSITY   |   CHANGE MANAGEMENT TOOLKIT

Training and Readiness Plan

Give people what they need to succeed before and during launch. Plan training by audience, then confirm readiness.

Training by audience

| Audience | What they need to learn | Format | When | Owner |
| --- | --- | --- | --- | --- |
| End users | The new day to day process | Demo plus job aid | 2 weeks before launch | Training Lead |
| People leaders | Their part and how to support the team | Short briefing | 3 weeks before | Change Lead |
| Super users | Deeper detail to support others | Hands on session | 3 weeks before | Functional Lead |

Delivery approach

Note how training will run: live, recorded, self paced, or a mix. Include where materials will live.

Readiness criteria

- All audiences have completed training or have access to it.

- Job aids and quick guides are published and easy to find.

- Super users are identified and ready to help.

- Support channels are set up and communicated.

Use the Go-Live Readiness Checklist to track these to done.